## Sheet1
|  | Description | Status
1 | Bug | a) Login screen sometimes gets stuck – at two times spent 30 seconds on the “Please wait while your data is being processed” b) Site moves very slowly sometimes (11:11am 3/14/2017) c) Logging in again takes very long time (12:27pm 3/14/2017) d) Logging in taking long again (1:25pm on 3/14/2017 e) Website takes long to load (1:50pm 3/14/2017) | Ongoing
2 | New | We can remove one space from here. Understand that it may affect a small number of items with 3 line descriptions but we will deal with that later. | DONE
3 | Question | a) When an item is on sale, there should only be ONE price showing. It should not say “As low as”. b) The “Price” should show the Sale Price, not the standard price | How We get the Sale Price for an Item ? Does the Sale price came from FACTS ?
4 | Question | a) I’ve mentioned this before b) I know the HTML5 does some stuff to the formatting, but there has to be some way to lock certain things in place. I reduced the browser size only slightly, and it starts doing all these weird formatting things i) Green Bar enlarges ii) Logo gets cutoff iii) Blue bar enlarges by a lot iv) Banners start stacking v) If we need to add those bars on the side of the site (like many sites c) We want to lock the site in place and people need to scroll left and right if they make the browser smaller. We don’t want it to wrap. d) Check out Mastercutlery.com on your phone browser – they have a separate mobile site that operates differently than their regular site. That’s what we should develop for phone and tablet users. | Faztrack will Discuss
5 | Question | "Sign Up for Newsletter" How do we connect this to constant contact? | Faztrack will Discuss
6 | Question | a) If an item is out of stock, it should not be adding to the order total b) It should be showing as 0 in the “Total” column | Faztrack will Discuss
7 | New | a) Descriptions should always be forced to start right under product description b) I think bringing the descriptions over, some of ours didn’t start on the first line because it didn’t matter before. | DONE
8 | New | a) Could you do a mock of moving the additional images to the left of the main picture? b) I don’t like the extra amount of white space on the left side of the screen c) This way, description will get moved up so customer can see everything on one screen, and there’s not lot of empty space | DONE
9 | Question | Can we force the system to update the item description format? See this description doesn’t have the font or font size of our normal description. | Faztrack will Discuss
10 | Bug | Confused about what’s going on here Total in corner reads $0.00 Out of stock items are getting calculated In stock items are being calculated But no addition is happening in card | Ongoing
11 | Bug | a) System MSG said I needed to get above $100 so I tried changing 203259 (the only in stock item) to 10 pcs and then I got this error b) Now when I try to clear, I get the same error 3) Eventually just logged out, and logged back in | Ongoing
12 | Bug | a) Before I have saved the cart b) Now I have saved the cart, but when I click “Continue with Saved Order”, it says “Please wait while the data is being processed”, and then nothing happens. I think when you click this, all the items should go back to the card and it should take you to the cart screen c) I clicked “Start New Order”, it took me back to the home screen, and then I somehow already have one item in my cart. Not sure why this is being pulling. d) Start New Order takes very long time to load | Ongoing
13 | Bug | When I click “Load Order to Cart”, it says “Wait for your data etc”, but then nothing happens. Shopping Cart total remains unchanged, and it doesn’t take me to the cart. It should take me to the cart with the order populated | Ongoing
14 | New | Card Holder Address Doesn’t need to be so big. It’s usually only one line | Done
15 | New | (Admin Portal) Can’t figure out how to add items to categories online Also I’m not sure if it gives me the option to automatically add to the main category For example, if I put a knife into the subcategory “Quick Assist Knives”, it should also go into the main category of “Knives” On the page “Product List Without Categories”, there’s no way to go into the item and add it to a category You have to go to the Categories page to add, which seems counterintuitive. I should be able to do it from both | Ongoing
16 | Question | (Admin Portal) Where do I approve customers who have requested Online Access to browse? (but not place an order, so they’re not going in FACTS yet) | Faztrack will Discuss
17 | New | (Admin Portal) I don’t see a breakdown for “Best Sellers” on the “Product Feature Settings” Page I think we will just delete this section and have it all just be “Featured” items Best Sellers also comes up when you click Special on the home page, it should only be “Special” | DONE
18 | New | On the master cutlery website, they have the ability to add an announcement as a pop-up – we want this also, like bad weather days | Ongoing